## FullWP
Scope of Work Element | Deliverable Action Items | Actions Planned | Supporting Resources or Collaboration Needs | Status Update- Provide Information Regarding SC Contributions | Status | Estimated Complete Date
1. Coordinate PRISM partner invasive species management activities | a. Collaborate with various stakeholder groups, community leaders, the New York State Invasive Species Advisory Committee, and other PRISMs and partners. | i. Attend invasive species-specific conferences and programs including the Cornell in-service conference. Attend PRISM leaders meetings. Participate in monthly invasive calls. Participate in various partner projects, Water Quality Coordinating Committee, etc. | Working groups, Steering Committee, partners, PRISM Coordinator, and stakeholders
|  | ii. Foster relationships and strengthen networks with partners in the Finger Lakes region | Steering Committee, Partners, FL-PRISM Coordinator
| b. Share information and resources within FL-PRISM | i. Coordinate Steering Committee and Working Group meetings and distribute minutes | SC, Listserve, Website
|  | ii. Coordinate Full Partnership Meetings (semi-annually) and distribute minutes to all partners | SC, DEC, all partners, Listserve, wesbite
| c. FL-PRISM-specific website | i. Create and Update a FL-specific website and update NYIS.INFO website as appropriate
| d. Develop social-media and outreach venues (Twitter, Facebook, etc) and garner support from partners | i. Create a Facebook page and promote FL-PRISM events. Create a Twitter page and promote FL-PRISM activities on news feed | Internet access, Facebook, Twitter and other social media outlets
| e. Identify needs for FL-PRISM | i. Hold Steering Committee and working group meetings regularly to identify needs and priorities. Present successeses to partners. | Working groups, Steering Committee, partners
|  | ii. Utilize listserve, partners, and website to help identify management, education, and outreach needs for the Finger Lakes PRISM | SC, CCE,
| f. Conduct regional invasive species management planning and create documentation as necessary | i. Utilize the state and federal IS documentation such as the early detection/rapid response management plan and update approaching regional lists via working groups | Working groups, Steering Committee, partners
| g. Highlight FL-PRISM success stories and challenges in IS management | i. Put success stories and challenges up on the FL-PRISM website and include in the annual report. Fill out the project management list with how the projects went. | Web site. Listserve. Annual report. Working Groups
| h. Provide MOU/Letters of Support from FL-PRISM partners to DEC OISC | i. Develop MOUs to be signed by partners or Letter of Support to be submitted to DEC OISC | PRISM Coordinator
2. Recruit and train volunteers | a. Organize training sessions on invasive species identification, monitoring, management and/or prevention | i. Provide iMapInvasives trainings for FL-PRISM regional volunteers | iMapInvasives
|  | ii. Support partner events and activities in the region | Website, listserve, calendar, partner communication
| b. Recruit volunteers | i. Identify, recruit, and maintain a list of volunteer groups, organizations and other partners interested in volunteering for IS management and remediation | Partners, Education and Outreach Working Group, CCE
|  | ii. Develop volunteer waiver form and standard operating procedure for volunteering | FLPRISM Coordinator, HWS
|  | iii. Organize and attend volunteer opportunities in the Finger Lakes region | Working groups, Steering Committee, partners
| c. Compile list of volunteer names, activities, and hours contributed to FL-PRISM projects | i. Maintain records of volunteers for projects/ create database/spreadsheet to track volunteer information | Working group reports, SC, others
|  | ii. Compile information for annual report | Coordinator and WGs
3. Identify and meet PRISM Education and Outreach needs | a. Track list of education programs offered, events attended, and/or materials produced. Quantify number of participants in attendence | i. create community calendar to create awareness of educational opportunities for the public | FLPRISM Support person
|  | ii. Create and maintain database of partner activities and keep track of events and hours of programs offered | Working groups, Steering Committee, partners
|  | iii. Compile results from partner reports and direct FL-PRISM activities, quantify # participants, etc. and send out report of activities | FLPRISM Coordinator
|  | iv. Compile information for annual report | FLPRISM Coordinator
| b. Determine Outreach needs and develop E & O materials and programs. | i. Set E & O priorities within E&OWG | E&OWG, USDA, DEC, TNC, CCE, Universities
|  | ii. Produce FL-PRISM-specific promotional material | E&OWG, DEC, CCE, E&O support
|  | iii. Develop/update/maintain outreach display material for use at events, fairs, conferences, etc. (banners, trifold material, etc) | E&OWG, NYS OPRHP, volunteer agencies, CCE, others
| c. Provide educational opportunuties for FL-PRISM | i. Offer IS workshops, forums, and presentations to the Finger Lakes region | Working groups, Steering Committee, partners
|  | ii. Collaborate and take part in community events to provide E&O to the FL-PRISM | E&OWG, stakholders
|  | iii. Attend and offer continuing education workshops and trainings | CCE, DEC
4. Establish monitoring network for early detection of invasive species | a. Establish volunteer monitoring network for ED/RR of IS | i. Train volunteers in iMap use and IS occurrence collection. | iMap, gps, CCE IST
|  | ii. Act as iMap liason for the region, reviewing reports. | iMap
|  | iii. Train volunteers, citizen scientists and resource managers in EDRR methods to report to Coordinator. | E&OWG, CCE, lake associations, NYSFOLA
|  | iv. Work with partners to engage volunteers in monitoring efforts | E&OWG, NYSFOLA, volunteer agencies, CCE, others
|  | v. Compile information for annual report | FLPRISM Coordinator
| b. Submit all invasive species occurrence data collected by FL-PRISM and IS control efforts to NYSISD (iMap) | i. Train volunteers in iMap use and IS occurrence collection. | imap, CCE, NYSDEC, nature preserves, etc.
5. Support academic research as needed through citizen science | a. Identify research needs for prevention, ED/RR and control of IS | i. Work with partners and Universities and Colleges to determine research needs | NYISRI, NYSDEC ISCU
| b. Support research projects in as such needs are identified. | i. Identify research topics that will directly impact management in the region | SC
|  | ii. Develop relationships with research institutions to build knowledge of IS issues in the region | SC, NYISRI
|  | iii. Attend and support reasearch conferences | Coordinator and WGs
|  | iv. Use the FL-PRISM list-serve as a tool for research questions and sharing of new findings | All
| c. Submit PRISM research priorities to the NYS Invasive Species Office of Invasive Species Coordination and include in annual report. | i. Submit PRISM research priorities to the NYS Invasive Species Office of Invasive Species Coordination and include in annual report. | Coordinator and WGs
6. Develop a PRISM Strategic Plan | a. Collect input from all partners and opportunity for all partners to contribute to plan | i. Provide opportunity for all partners to provide input and contribute
ii. Discuss revisions in committee and develop a second draft to distribute to all partners for review.
iii. Incorporate partner revisions and distribute for final review session to be held at winter meeting
iv. Release final version
| b. Use a format that will be cooperatively developed by the OISC and coordinated with other PRISMs | We plan to use the OISC template for strategic plan
| c. Engage citizens through regular outreach to potential members, partners and volunteers | i. Invite potential new members to attend FL-PRISM meetings | WGs, SC, CCE, NYSDEC, others
|  | ii. Have FL-PRISM presence at events throughout the region to engage new members and volunteers | CCE, DEC, OPRHP, Interns, HRM, Working Groups
| d. Develop prioritized goals based on PRISM core functions and mission | i. Work with partners to identify main goals and prioritize them
ii. Articulate prioritized goals to the public through education and outreach
| e. Submit Strategic Plan to OISC Coordinator | i. Once it has been finalized, submit to OISC
7. Develop FL-PRISM-specific IS Management Plan | a. Using Strategic Plan (SP) goals, identify management needs | i. Work with partners to determine management needs based on goals
| b. Develop measurable, acheivable and prioritzed objectives to attain goals | i. Work with partners to identify smart objectives, through logic model format
| c. Identify specific actions to achieve objectives and measures to evaluate progress | i. Work with partners to identify actions and measures to go with each objective identified
| d. Use format established by OISC | i. Use the OISC template for management plans | NYSDEC ISCU
8. Implement eradication projects to remove invasives species | a. Coordinate PRISM partners to conduct eradication projects for IS using BMPs and adaptable approachs as soon as possible after detection | i.Update FL-PRISM species list, including known established invasive species, early detection species, and approaching region species. | NYSDEC, WGs, NYSFOLA, NYFOA, etc.
ii. Ensure use of Best Management Practices for eradication efforts and be sure that they are consisten with SP and ISMP
iii. Compile resources on website to help with identifying BMPs for management for species listed.
| b. Summarize species eradication projects and incorporate into annual report | i. Develop a form for partners to detail all control efforts.
ii. Compile information for annual report
9. Develop annual work plan | a. Plan should be based on priority objectives once IS Management plan is developed | i. Rework work plan once IS Management plan is developed
|  | ii. Develop and complete 2016-2017 work plan | Steering Committee
| b. develop 2017 Annual Work Plan | i. Utilizing the Steering Committee, develop, create draft and complete 2017 Annual Work Plan | Steering Committee
10. Develop annual report to include: | a. Progress toward accomplishing priority objectives from the IS Management Plan | i. Use objectives from IS Management plan to measure progress and include in 2017 Annual Report
| b. Results of eradication and control efforts | i. Solicit feedback from partners regarding all 2017-18 eradication efforts to include in 2017 annual report
ii. Maintain records of all eradication and control efforts since 2013 to include in report
| c. Descriptions of obstacles to achieving objectives and any revisions or resources needed to further the objectives | i. Assess progress and determine what obstacles have been met in trying to achieve objectives
| d. Potential solutions to obstacles and/or resources needed to accomplish priority objectives | i. Determine potential solutions to obstacles
| e. Scope of Work Elements, 2, 3, 4, 5, 8,12,13 | i. Report as mentioned in each of the scope of work elements
| f. Summary of project expenses | i. Track all expenses and compile into summary document
g. Submit to OISC
11. Coordinate access to private and public lands | a. Answer requests for access to public and private lands for IS management activities | i. Make partners aware that they should go through FL-PRISM to get access for IS management | SWCD
ii. Develop contacts for public lands where IS management activities are ongoing
iii. Assist partners with property owner permission for access
iv. Develop standard operarting procedure for coordinating access to lands for invasive species management activities.
12. Coordinate with other PRISMs and OISC | a. Provide PRISM updates or identify a proxy to provide updates for monthly NYS Invasive Species calls, quarterly PRISM coordinator calls and as needed | i. Call in to provide monthly/quarterly updates
ii. Communicate with other PRISMs and OISC as needed to discuss PRISM issues and concerns
|  | iii. Communicate with PRISM leaders and attend conferences, symposiums, workshops in other PRISMs as appropriate | PRISM
| b. Summarize in annual report | i. Keep records of monthly updates and summarize for annual report
13. Support NY ISC regular invasive species conference | a. Support conference through planning, presentations, contributed papers, posters, and workshops. | i. Assist with either ISC conference or other IS conferences.
ii. Encourage partners to submit presentations, papers, posters, etc.
| b. Summarize in annual report | i. Track all conference activities and include in annual report
Other: Add notes here

## Top13
Scope of Work Element
1. Coordinate PRISM partner invasive species management activities
2. Recruit and train volunteers
3. Identify and meet PRISM Education and Outreach needs
4. Establish monitoring network for early detection of invasive species
5. Support academic research as needed through citizen science
6. Develop a PRISM Strategic Plan
7. Develop FL-PRISM-specific IS Management Plan
8. Implement eradication projects to remove invasives species
9. Develop annual work plan
10. Develop annual report to include:
11. Coordinate access to private and public lands
12. Coordinate with other PRISMs and OISC
13. Support NY ISC regular invasive species conference