## 2019WorkPlan
2019 Work Plan
| Objectives and Strategies | Supporting Actions | Lead | Status Update | Estimated Date of Completion |  | Yr 1 % | Yr 2 % | Yr 3 % | Yr 4 % | Yr 5 % | TOTAL
GOAL #1 Prevention
Objective 1A | The community is knowledgeable about priority organisms, the pathways of invasion, and the likeliness of invasion and acts in a manner that prevents the spread of invasive species | [5 empty] | 5 | 10 | 25 | 30 | 30 | 100
| Identify and provide outreach to target audiences including, but not limited to: anglers, recreationists and hikers, with information tailored to the various vectors of transmission | Organize training sessions and support partner events
| Develop, promote, and evaluate volunteer program that effectively monitor areas and creates awareness | Identify, recruit, and maintain list of volunteers, organizations and other partners interested in volunteering | [6 empty] | Support | social media, E&OWG,
| Support existing state, federal, and location prevention and prevention programs | Participate in NYISAW and other IS campaigns
| Create Invasive Species Prevention Zones (ISPZ) that are at a great risk for a large negative impact from invasive species | Develop an ISPZ criteria list and designate ISPZ
Objective 1B | The FL-PRISM partnership shares resources and information regarding prevention management and control methods | [5 empty] | 10 | 15 | 20 | 25 | 30 | 100
| Establish, facilitate, and support a platform for sharing of surveillance data/ED data | Support iMapinvasives program and upload data as appropriate | [6 empty] | Support | Coordinator
| Help create or support easy to use identification (ID) tools for public reference and use | Develop/update/maintain outreach display material for use at events, fairs, conferences, etc. (banners, trifold material, etc) | [6 empty] | Support | Coordinator
| Utilize communication networks to publicize prevention techniques for highly invasive species that have the potential for great economic, human health, and ecosystem harm to other localities | Utilize the website, listserve, and social media to disseminate information to the region
| Communicate with other PRISM leaders | Work with PRISM leaders and attand statewide meetings for forest health, aquatic invasive species, etc. |  |  |  | Coordination/Partnership
GOAL #2 Coordination/Partnership | [6 empty] | Yr 1 % | Yr 2 % | Yr 3 % | Yr 4 % | Yr 5 % | TOTAL
Objective 2A | FL-PRISM partners represent key stakeholders in the Finger Lakes region | [5 empty] | 1 | 10 | 25 | 30 | 34 | 100
Recruit key partners not already engaged in the FL-PRISM to become part of the partnership
Identify partner contributions and capacity for the different strategies identified in the strategic plan and to host educational activities, exhibits, and creation of materials
Objective 2B | Partners share strengths to reach common goals
Create and maintain a database of current resources and research on specific organisms of concern to help with education, outreach, management, and prevention
Objective 2C | Partners share resources such as information, data, and materials to reduce costs and eliminate duplication of efforts
Maintain communication and relationship with partners through listserve, social media and other forms of communication to encourage participation in IS activities (NYS ISAW), meetings, and reporting
| Facilitate networking through full partnership meetings, working groups, email listserves, and other appropriate communication avenues | [5 empty] | 1 | 10 | 25 | 30 | 34 | 100
GOAL #3 Early Detection/Rapid Response Assessment | [5 empty] | Early Detection/Rapid Response Assessment | [5 empty] | 0
Objective 3A | FL-PRISM partners use an effective ED/RR process | [5 empty] | 1 | 10 | 19 | 30 | 40 | 100
Develop a protocol for reporting, confirming, and identifying a new population or new invasive
Utilize the FL-PRISM website as a platform for sharing of surveillance data and ED data
Create easy to use early detection identification tools for public reference
Train volunteers/public (e.g., Master Gardeners) in early detection invasives
Objective 3B | FL-PRISM identify and support the continuous monitoring of priority areas for highly invasive or early detection species
| Identify costs associated with an ED/RR program and potential funding opportunities | [5 empty] | 1 | 10 | 19 | 20 | 20 | 70
Utilize students or interns to survey and monitor for high priority species
Objective 3C | The community is knowledgeable about priority early detection organisms and those regulated by the nursery trade, the likeliness of invasion, and the vector of transmission
Work with permitting agencies to streamline the permitting process to ensure rapid response to potential invasion
Develop list of known distribution of priority invasives within region and identify survey needs
| Utilize communication networks to advertise new infestations that have the potential for great economic, human health, and ecosystem harm to other localities | [5 empty] | 0 | 20 | 20 | 30 | 30 | 100
GOAL #4 Education and Outreach | [5 empty] | Education and Outreach
Objective 4A | Create and maintain consistent messaging that uses the best available materials and methods regarding the FL-PRISM and IS prevention, impacts, and management options | [5 empty] | 1 | 10 | 19 | 30 | 40 | 100
Identify existing educational materials and messaging of IS within the Finger Lakes region and nationwide
Utilize the best available materials and existing state and national public education campaigns (Don’t Move Firewood, Stop Aquatic hitchhikers, PlayCleanGo)
Identify gaps in education and outreach materials and work with partners to create diversified tools for outreach such as social media, train the trainer programs, and a list of guest speakers with an expertise in invasive species
Create and promote FL-PRISM branding/marketing initiative
Encourage partners and stakeholders to link to FL-PRISM website
Create and utilize an educational toolbox to provide public with appropriate IS response tools
Utilize social media to disseminate information about invasive species and vectors of transmission to the greater public
Objective 4B | The public makes choices that prevent IS introduction and spread | [5 empty] | 1 | 10 | 19 | 30 | 40 | 100
Provide workshops or forums for stakeholders to ensure knowledge and resources are shared and consistent
Use selected materials to reach stakeholders, venues and events that are prioritized in management plans and strategies from other goals
Use community presentations (i.e., annual meetings, garden clubs, hunting and angler associations, etc.) to disseminate information to general audiences; use academic institutions for community presentations/resource to disseminate information
Objective 4C | The public knows about the FL-PRISM
Support state, federal, and local education and outreach programs
Use train the trainer model of outreach to increase the reach of the FL-PRISM
| Work with school districts to incorporate IS awareness in curriculum | [5 empty] | 1 | 19 | 25 | 25 | 30 | 100
Use evaluation techniques such as surveys, to access effectiveness of educational campaigns on behavior change
Promote FL-PRISM as a partner for all education and outreach in the Finger Lakes region
Create a list of experts to draw on as speakers and sources of information /resources
GOAL #5 Information Management and Communication | [5 empty] | Information Management and Communication
Objective 5A | The FL-PRISM will have a fully-utilized and robust web presence | [5 empty] | 1 | 10 | 20 | 29 | 40 | 100
Partners utilize the FL-PRISM website as the premiere location for all information on invasive species within the Finger Lakes region and beyond
Synthesize and disseminate watercraft steward/boat steward data to the public via the FL-PRISM website
Develop a consistent marketing strategy to convey the importance of watercraft stewards to the public (i.e., Clean, Drain, Dry!, Stop Aquatic Hitchikers!)
Objective 5B | Develop and promote use of IS materials, protocols and fact sheets
Create opportunities for partners to share information and resources
Develop a marketing and communication strategy, including a robust and all-inclusive website, to enable the community to recognize and consider FL-PRISM as the entity for information, management ideas, ED/RR, and all things invasive in the region
Develop a prevention, management, and work plan that brings together various stakeholders to establish the synergy necessary to tackle IS within the community through a clear and concise strategies for prevention, control, and remediation.
| Develop a FL-PRISM resource guide for partners to include resources, capacity and partner capabilities within the region | [5 empty] | 1 | 10 | 32 | 33 | 33 | 109
Objective 5C | Encourage invasive species reporting and information sharing
Develop a matrix to use when determining priority organisms and locations for AIS invasion and management
Goal #6. Invasive Species Control Measures and Restoration | [5 empty] | GOAL #6 Invasive Species Control Measures and Restoration | Yr 1 % | Yr 2 % | Yr 3 % | Yr 4 % | Yr 5 % | TOTAL
Objective 6A | Resources are prioritized to address high impact IS projects | [5 empty] | 1 | 19 | 20 | 30 | 30 | 100
Develop a priority species and areas list for the FL region
FL-PRISM subcontract awards are prioritized to provide resources to high impact and demonstration projects in the region
Develop list of potential funding opportunities and disseminate on the FL-PRISM website
Secure funding to implement control and restoration projects within the Finger Lakes
Coordinate projects with partners to eliminate duplication of efforts and leverage support
Objective 6B | Invasive Species are stopped from spreading along predictable corridors | [5 empty] | 1 | 19 | 20 | 30 | 30 | 100
Develop strategies for working with private landowners in targeted high priority areas
Create a management plan and annual work plan to be carried out by FL-PRISM partners
Identify site and species-specific best management practices
Develop a management plan to include restoration of areas where invasives have been removed
Identify likely transport corridors for prioritized projects
Objective 6C | Isolated outbreaks of IS are restricted from spreading | [5 empty] | 1 | 19 | 20 | 30 | 30 | 100
Identify and obtain needed resources for eradication, containment, suppression, and restoration
Isolated outbreaks of priority IS are prioritized for control and restoration
Goal 7. Legislation and Support: Federal, state, and local governments support | [5 empty] | GOAL #7 Legislation and Support: Federal, state, and local governments support | Yr 1 % | Yr 2 % | Yr 3 % | Yr 4 % | Yr 5 % | TOTAL
Objective 7A | FL-PRISM members have relationships with key governmental entities that influence IS | [5 empty] | 1 | 10 | 10 | 30 | 49 | 100
Identify and learn about entities with regulatory, enforcement or funding influence, including knowing key contacts and people of influence
Develop and maintain a line of communication to stakeholders
Invite State/County/Local highway departments to partner with FL-PRISM
Objective 7B | FL-PRISM influences IS legislation | [5 empty] | 1 | 10 | 20 | 30 | 39 | 100
Establish a FL-PRISM legislative liaison
| Provide information on IS management to governmental agencies including the importance of long-term, consistent funding |  |  |  |  | Strategy to complete goal |  |  | Support | Coordinator, WGs |  |  |  | Strategy to complete goal |  | Develop, promote, and evaluate volunteer program that effectively monitor areas and creates awareness |  |  | Support | E&OWG, LA, NYSFOLA, NYFOA, CCE
| Communicate with stakeholders on legislative initiatives and proposed regulations |  |  |  |  | Strategy to complete goal |  |  | Support | Coordinator, SC |  |  |  | Strategy to complete goal |  | Establish, facilitate, and support a platform for sharing of surveillance data/ED data |  |  | Support | iMapInvasives, FL-PRISM website,
| Actively review and provide comments as appropriate on proposed and existing regulations that affect invasive species |  |  |  |  | Strategy to complete goal |  |  | Support | Coordinator, SC, WGs, Partners |  |  |  | Strategy to complete goal |  | Help create or support easy to use identification (ID) tools for public reference and use |  |  | Support | AqWG, TWG, E&OWG, DOT, NYS DEC
Objective 7C | Secure adequate funding to support the mission of the FL-PRISM | [5 empty] | 1 | 20 | 20 | 20 | 39 | 100
| Actively support stakeholders in contacting appropriate government agencies/representatives | [12 empty] | Strategy to complete goal |  | Create Invasive Species Prevention Zones (ISPZ) that are at a great risk for a large negative impact from invasive species |  |  | Support | AqWG, TWG
| Work with partners to identify and pursue funding resources | [12 empty] | Strategy to complete goal |  | Communicate with other PRISM leaders |  |  | Support | Coordinator
| Stay current on opportunities of Federal and State funding resources | [12 empty] | Strategy to complete goal |  | Support existing state, federal, and location prevention and prevention programs |  |  | Support | Coordinator
| Disseminate funding opportunity information to FL-PRISM listserve | [12 empty] | Coordination/Partnership | [7 empty] | 0
| Identify “shovel ready” projects for funding applications | [12 empty] | GOAL #2 Coordination/Partnership |  |  | Yr 1 % | Yr 2 % | Yr 3 % | Yr 4 % | Yr 5 % | TOTAL
| Explore various fundraising opportunities such as special events | [12 empty] | Objective 1 | FL-PRISM partners represent key stakeholders in the Finger Lakes region |  | 1 | 10 | 25 | 30 | 34 | 100
| Seek external funding sources for invasive species research, control, and prevention within the FL-region | [12 empty] | Objective 2 | Partners share strengths to reach common goals |  | 1 | 10 | 25 | 30 | 34 | 100
[14 empty] | Objective 3 | Partners share resources such as information, data, and materials to reduce costs and eliminate duplication of efforts |  | 1 | 10 | 20 | 30 | 34 | 95
[14 empty] | Strategy to complete goal |  | Recruit key partners not already engaged in the FL-PRISM to become part of the partnership |  |  | Support | Coordinator, SC, WG, Partners
[14 empty] | Strategy to complete goal |  | Maintain communication and relationship with partners through listserve, social media and other forms of communication to encourage participation in IS activities (NYS ISAW), meetings, and reporting |  |  | Support | Coordinator, CCE, listserves
[14 empty] | Strategy to complete goal |  | Facilitate networking through full partnership meetings, working groups, email listserves, and other appropriate communication avenues |  |  | Support | Coordinator
[14 empty] | Strategy to complete goal |  | Identify partner contributions and capacity for the different strategies identified in the strategic plan and to host educational activities, exhibits, and creation of materials |  |  | Support | Coordinator, SC
[14 empty] | Strategy to complete goal |  | Create and maintain a database of current resources and research on specific organisms of concern to help with education, outreach, management, and prevention |  |  | Support | WGs, partners
[14 empty] | Early Detection/Rapid Response Assessment | [7 empty] | 0
[13 empty] | GOAL #3 Early Detection/Rapid Response Assessment |  |  |  | Yr 1 % | Yr 2 % | Yr 3 % | Yr 4 % | Yr 5 % | TOTAL
[14 empty] | Objective 1 | FL-PRISM partners use an effective ED/RR process |  | 1 | 10 | 19 | 30 | 40 | 100
[14 empty] | Objective 2 | FL-PRISM identify and support the continuous monitoring of priority areas for highly invasive or early detection species |  | 1 | 10 | 19 | 20 | 20 | 70
[14 empty] | Objective 3 | The community is knowledgeable about priority early detection organisms and those regulated by the nursery trade, the likeliness of invasion, and the vector of transmission |  | 0 | 20 | 20 | 30 | 30 | 100
[14 empty] | Strategy to complete goal |  | Develop a protocol for reporting, confirming, and identifying a new population or new invasive |  |  | Support | Coordinator with support from WG
[14 empty] | Strategy to complete goal |  | Utilize the FL-PRISM website as a platform for sharing of surveillance data and ED data |  |  | Support | LA, NYSFOLA, NYSFOA, ADK, CCE, SWCD
[14 empty] | Strategy to complete goal |  | Identify costs associated with an ED/RR program and potential funding opportunities |  |  | Support | All, Coordinator,
[14 empty] | Strategy to complete goal |  | Work with permitting agencies to streamline the permitting process to ensure rapid response to potential invasion |  |  | Support | WGs, NYS DEC, SWCD
[14 empty] | Strategy to complete goal |  | Develop list of known distribution of priority invasives within region and identify survey needs |  |  | Support | WGs, WQCC, SWCD
[14 empty] | Strategy to complete goal |  | Utilize students or interns to survey and monitor for high priority species |  |  | Support | WGs
[14 empty] | Strategy to complete goal |  | Create easy to use early detection identification tools for public reference |  |  | Support | Coordinator, WGs, CCE,
[14 empty] | Strategy to complete goal |  | Train volunteers/public (e.g., Master Gardeners) in early detection invasives |  |  | Support | Coordinator, E&OWG, CCE
[14 empty] | Strategy to complete goal |  | Utilize communication networks to advertise new infestations that have the potential for great economic, human health, and ecosystem harm to other localities |  |  | Support | Coordinator
Education and Outreach
[14 empty] | GOAL #4 Education and Outreach |  |  | Yr 1 % | Yr 2 % | Yr 3 % | Yr 4 % | Yr 5 % | TOTAL
[14 empty] | Objective 1 | Create and maintain consistent messaging that uses the best available materials and methods regarding the FL-PRISM and IS prevention, impacts, and management options |  | 1 | 10 | 19 | 30 | 40 | 100
[14 empty] | Objective 2 | The public makes choices that prevent IS introduction and spread |  | 1 | 10 | 19 | 30 | 40 | 100
[14 empty] | Objective 3 | The public knows about the FL-PRISM |  | 1 | 19 | 25 | 25 | 30 | 100
[14 empty] | Strategy to complete goal |  | Identify existing educational materials and messaging of IS within the Finger Lakes region and nationwide |  |  | Support | E&OWG, LA, NYSFOLA, NYFOA, CCE
[14 empty] | Strategy to complete goal |  | Utilize the best available materials and existing state and national public education campaigns (Don’t Move Firewood, Stop Aquatic hitchhikers, PlayCleanGo) |  |  | Support | E&OWG, LA, NYSFOLA, NYFOA, CCE
[14 empty] | Strategy to complete goal |  | Identify gaps in education and outreach materials and work with partners to create diversified tools for outreach such as social media, train the trainer programs, and a list of guest speakers with an expertise in invasive species |  |  | Support | E&OWG, Coordinator
[14 empty] | Strategy to complete goal |  | Provide workshops or forums for stakeholders to ensure knowledge and resources are shared and consistent |  |  | Support | WGs, Coordinator, CCE, NYSFOLA, NYSFOA
[14 empty] | Strategy to complete goal |  | Support state, federal, and local education and outreach programs |  |  | Support | Coordinator, WGs, CCE,
[14 empty] | Strategy to complete goal |  | Use selected materials to reach stakeholders, venues and events that are prioritized in management plans and strategies from other goals |  |  | Support | Coordinator, WGs, CCE,
[14 empty] | Strategy to complete goal |  | Use train the trainer model of outreach to increase the reach of the FL-PRISM |  |  | Support | Coordinator, CCE, NYSFOLA, NYSFOA
[14 empty] | Strategy to complete goal |  | Work with school districts to incorporate IS awareness in curriculum |  |  | Support | E&OWG, NYS DEC, Environmental Educators
[14 empty] | Strategy to complete goal |  | Use evaluation techniques such as surveys, to access effectiveness of educational campaigns on behavior change |  |  | Support | Coordinator
[14 empty] | Strategy to complete goal |  | Create and promote FL-PRISM branding/marketing initiative |  |  | Support | All, Coordinator,
[14 empty] | Strategy to complete goal |  | Encourage partners and stakeholders to link to FL-PRISM website |  |  | Support | All
[14 empty] | Strategy to complete goal |  | Promote FL-PRISM as a partner for all education and outreach in the Finger Lakes region |  |  | Support | All
[14 empty] | Strategy to complete goal |  | Create and utilize an educational toolbox to provide public with appropriate IS response tools |  |  | Support | Coordinator, WGs, CCE,
[14 empty] | Strategy to complete goal |  | Create a list of experts to draw on as speakers and sources of information /resources |  |  | Support | Coordinator, SC, WG, Partners
[14 empty] | Strategy to complete goal |  | Utilize social media to disseminate information about invasive species and vectors of transmission to the greater public |  |  | Support | All
[14 empty] | Strategy to complete goal |  | Use community presentations (i.e., annual meetings, garden clubs, hunting and angler associations, etc.) to disseminate information to general audiences; use academic institutions for community presentations/resource to disseminate information |  |  | Support | All
Information Management and Communication
[14 empty] | GOAL #5 Information Management and Communication |  |  | Yr 1 % | Yr 2 % | Yr 3 % | Yr 4 % | Yr 5 % | TOTAL
[14 empty] | Objective 1 | The FL-PRISM will have a fully-utilized and robust web presence |  | 1 | 10 | 20 | 29 | 40 | 100
[14 empty] | Objective 2 | Develop and promote use of IS materials, protocols and fact sheets |  | 1 | 10 | 32 | 33 | 33 | 109
[14 empty] | Objective 3 | Encourage invasive species reporting and information sharing |  | 20 | 20 | 20 | 20 | 20 | 100
[13 empty] | Strategy to complete goal |  |  | Create opportunities for partners to share information and resources |  |  | Support | Coordinator
[13 empty] | Strategy to complete goal |  |  | Partners utilize the FL-PRISM website as the premiere location for all information on invasive species within the Finger Lakes region and beyond |  |  | Support | All
[13 empty] | Strategy to complete goal |  |  | Develop a marketing and communication strategy, including a robust and all-inclusive website, to enable the community to recognize and consider FL-PRISM as the entity for information, management ideas, ED/RR, and all things invasive in the region |  |  | Support | Coordinator, WGs, CCE,
[13 empty] | Strategy to complete goal |  |  | Synthesize and disseminate watercraft steward/boat steward data to the public via the FL-PRISM website |  |  | Support | NYSFOLA, FLI, LA, WCS programs
[13 empty] | Strategy to complete goal |  |  | Develop a consistent marketing strategy to convey the importance of watercraft stewards to the public (i.e., Clean, Drain, Dry!, Stop Aquatic Hitchikers!) |  |  | Support | Coordinator, SC, WG, Partners
[13 empty] | Strategy to complete goal |  |  | Develop a prevention, management, and work plan that brings together various stakeholders to establish the synergy necessary to tackle IS within the community through a clear and concise strategies for prevention, control, and remediation. |  |  | Support | Coordinator, SC, WG, Partners
[13 empty] | Strategy to complete goal |  |  | Develop a FL-PRISM resource guide for partners to include resources, capacity and partner capabilities within the region |  |  | Support | Coordinator
[13 empty] | Strategy to complete goal |  |  | Develop a matrix to use when determining priority organisms and locations for AIS invasion and management |  |  | Support | Coordinator, WGs, CCE,
Invasive Species Control Measures and Restoration
[14 empty] | GOAL #6 Invasive Species Control Measures and Restoration |  |  | Yr 1 % | Yr 2 % | Yr 3 % | Yr 4 % | Yr 5 % | TOTAL
[14 empty] | Objective 1 | Resources are prioritized to address high impact IS projects |  | 1 | 19 | 20 | 30 | 30 | 100
[14 empty] | Objective 2 | Invasive Species are stopped from spreading along predictable corridors |  | 1 | 19 | 20 | 30 | 30 | 100
[14 empty] | Objective 3 | Isolated outbreaks of IS are restricted from spreading |  | 1 | 19 | 20 | 30 | 30 | 100
[14 empty] | Strategy to complete goal |  | Develop strategies for working with private landowners in targeted high priority areas |  |  | Support | NYSFOA, NYSFOLA, NYS DEC, Coordinator, CCE
[14 empty] | Strategy to complete goal |  | Develop a priority species and areas list for the FL region |  |  | Support | Coordinator, WGs, CCE,
[14 empty] | Strategy to complete goal |  | Create a management plan and annual work plan to be carried out by FL-PRISM partners |  |  | Support | Coordinator, SC
[14 empty] | Strategy to complete goal |  | Identify and obtain needed resources for eradication, containment, suppression, and restoration |  |  | Support | Coordinator, SC, WG, Partners
[14 empty] | Strategy to complete goal |  | FL-PRISM subcontract awards are prioritized to provide resources to high impact and demonstration projects in the region |  |  | Support | Coordinator, SC
[14 empty] | Strategy to complete goal |  | Develop list of potential funding opportunities and disseminate on the FL-PRISM website |  |  | Support | Coordinator, SC, WG, Partners
[14 empty] | Strategy to complete goal |  | Secure funding to implement control and restoration projects within the Finger Lakes |  |  | Support | Coordinator, SC, WG, Partners
[14 empty] | Strategy to complete goal |  | Isolated outbreaks of priority IS are prioritized for control and restoration |  |  | Support | Coordinator, WGs, CCE,
[14 empty] | Strategy to complete goal |  | Identify site and species-specific best management practices |  |  | Support | Coordinator, WGs, CCE,
[14 empty] | Strategy to complete goal |  | Develop a management plan to include restoration of areas where invasives have been removed |  |  | Support | Coordinator, SC, WG, Partners
[14 empty] | Strategy to complete goal |  | Coordinate projects with partners to eliminate duplication of efforts and leverage support |  |  | Support | Coordinator, SC, WG, Partners
[14 empty] | Strategy to complete goal |  | Identify likely transport corridors for prioritized projects |  |  | Support | Coordinator, WGs
Legislation and Support: Federal, state, and local governments support
[14 empty] | GOAL #7 Legislation and Support: Federal, state, and local governments support |  |  | Yr 1 % | Yr 2 % | Yr 3 % | Yr 4 % | Yr 5 % | TOTAL
[14 empty] | Objective 1 | FL-PRISM members have relationships with key governmental entities that influence IS |  | 1 | 10 | 10 | 30 | 49 | 100
[14 empty] | Objective 2 | FL-PRISM influences IS legislation |  | 1 | 10 | 20 | 30 | 39 | 100
[14 empty] | Objective 3 | Secure adequate funding to support the mission of the FL-PRISM |  | 1 | 20 | 20 | 20 | 39 | 100
[14 empty] | Strategy to complete goal |  | Identify and learn about entities with regulatory, enforcement or funding influence, including knowing key contacts and people of influence |  |  | Support | Coordinator, SC, WG, Partners
[14 empty] | Strategy to complete goal |  | Establish a FL-PRISM legislative liaison |  |  | Support | Coordinator, WGs
[14 empty] | Strategy to complete goal |  | Develop and maintain a line of communication to stakeholders |  |  | Support | Coordinator
[14 empty] | Strategy to complete goal |  | Invite State/County/Local highway departments to partner with FL-PRISM |  |  | Support | Coordinator, SC, WG, Partners
[14 empty] | Strategy to complete goal |  | Provide information on IS management to governmental agencies including the importance of long-term, consistent funding |  |  | Support | Coordinator, SC, WG, Partners
[14 empty] | Strategy to complete goal |  | Communicate with stakeholders on legislative initiatives and proposed regulations |  |  | Support | Coordinator, NYS DEC
[14 empty] | Strategy to complete goal |  | Actively review and provide comments as appropriate on proposed and existing regulations that affect invasive species |  |  | Support | Coordinator, Partners
[14 empty] | Strategy to complete goal |  | Actively support stakeholders in contacting appropriate government agencies/representatives |  |  | Support | Coordinator
[14 empty] | Strategy to complete goal |  | Work with partners to identify and pursue funding resources |  |  | Support | Coordinator
[14 empty] | Strategy to complete goal |  | Stay current on opportunities of Federal and State funding resources |  |  | Support | Coordinator, listserve
[14 empty] | Strategy to complete goal |  | Disseminate funding opportunity information to FL-PRISM listserve |  |  | Support | Coordinator, WGs, listserve
[14 empty] | Strategy to complete goal |  | Identify “shovel ready” projects for funding applications |  |  | Support | Coordinator, WGs
[14 empty] | Strategy to complete goal |  | Explore various fundraising opportunities such as special events |  |  | Support | Coordinator, SC
[14 empty] | Strategy to complete goal |  | Seek external funding sources for invasive species research, control, and prevention within the FL-region |  |  | Support | Coordinator, SC, WGs, Partners

## Sheet2
GOAL | Strategic Action to accomplish goal | Target # | Lead | Support | Stakeholder | Timeframe | Outcome | Future Strategy | Link to FL-PRISM Strategic Plan
Acres of water chestnut removed throughout the NYS Great Lakes Basin in targeted areas, and potential for greater acreage removed in areas surveyed | [8 empty] | 1,2,3,5,6 | GOAL #1 Prevention | Objective 1 | The community is knowledgeable about priority organisms, the pathways of invasion, and the likeliness of invasion and acts in a manner that prevents the spread of invasive species | Objective 2 | The FL-PRISM partnership shares resources and information regarding prevention management and control methods
Grade 6-12 students engaged in experiential, project-based learning regarding water chestnut, aquatic invasive species, and adopt-a-shoreline project | [8 empty] | 1,2,3,4,5 | GOAL #2 Coordination/Partnership | Objective 1 | FL-PRISM partners represent key stakeholders in the Finger Lakes region | Objective 2 | Partners share strengths to reach common goals | Objective 3 | Partners share resources such as information, data, and materials to reduce costs and eliminate duplication of efforts
Homeowners and boat slip users will be engaged about the negative impacts of water chestnut and through tips for removal and shoreline morning | [8 empty] | 1,2,3,4,5 | GOAL #3 Early Detection/Rapid Response Assessment | Objective 1 | FL-PRISM partners use an effective ED/RR process | Objective 2 | FL-PRISM identify and support the continuous monitoring of priority areas for highly invasive or early detection species | Objective 3 | The community is knowledgeable about priority early detection organisms and those regulated by the nursery trade, the likeliness of invasion, and the vector of transmission
Homeowners and boat slip users will participate in a training and commit to an adopt-a-shoreline model for monitoring and control of invasive species within the region | [8 empty] | 1,2,3,4,5 | GOAL #4 Education and Outreach | Objective 1 | Create and maintain consistent messaging that uses the best available materials and methods regarding the FL-PRISM and IS prevention, impacts, and management options | Objective 2 | The public makes choices that prevent IS introduction and spread | Objective 3 | The public knows about the FL-PRISM
Community members reached through events such as the NYS Fair and National Hunting and Fishing Days | [8 empty] | 1,2,3,4,5 | GOAL #5 Information Management and Communication | Objective 1 | The FL-PRISM will have a fully-utilized and robust web presence | Objective 2 | Develop and promote use of IS materials, protocols and fact sheets | Objective 3 | Encourage invasive species reporting and information sharing
A NYS Great Lakes Basin -specific waterproof field guide will be created and disseminated across the region and made available through established networks such as the FL-PRISM, New York State Federation of Lake Associations, North American Lake Management Society, and Midwest Invasive Plant Network | [8 empty] | 1,2,3,4,5, | GOAL #6 Invasive Species Control Measures and Restoration | Objective 1 | Resources are prioritized to address high impact IS projects | Objective 2 | Invasive Species are stopped from spreading along predictable corridors | Objective 3 | Isolated outbreaks of IS are restricted from spreading
[10 empty] | GOAL #7 Legislation and Support: Federal, state, and local governments support | Objective 1 | FL-PRISM members have relationships with key governmental entities that influence IS | Objective 2 | FL-PRISM influences IS legislation | Objective 3 | Secure adequate funding to support the mission of the FL-PRISM
Water chestnut and other aquatic invasive species will be documented through iMapInvasive website
Increased capacity of the FL-PRISM network via collaboration of 1.5 FTEs from the engagement of the project manager and education and outreach coordinator in various working groups
Adopt-a-shoreline model of community engagement is actively used throughout New York’s Great Lakes Basin
OUTPUTS | How is this documented/verified
Water quality of areas previously infested with water chestnut increased (increased biodiversity, increased dissolved oxygen, increased habitat quality for organisms)
Potential for new invasions of water chestnut across the region diminished #stoptheinvasion
Community is knowledgeable about water chestnut, control methods, and how to #stoptheinvasion of aquatic invasive species
fingerlakesinvasives.org website is the key website for information about water chestnut in the Finger Lakes region
Community is knowledgeable about populations of invasive species within the region and take action to #stoptheinvasion
Community acts in a manner to reduce encountered invasive species due to increased knowledge of issue.
Students have the necessary tools to #stoptheinvasion and teach others